## ChillFood.com
ChillFood.com
Sprint #2 Backlog
https://trello.com/b/5tEQHZBy
List | Title | Points | Members | Description | Card URL
Sprint 2 | Follow User | 2 | AA | Add ability to follow other users Display list of followers on the profile page Display list of followees on the profile page | https://trello.com/c/dNXRE3r3
Sprint 2 | Forgot Password | 2 | AA | User should be able to: - Reset their password once they are logged - Reset their password when they are not logged | https://trello.com/c/fNzLlqp8
Sprint 2 | Detail Recipe: Ask Friends Nearby | 8 | CP | User should be able to: - Ask friends to join him for a "Cooking Party" - Specify a "Cooking Party" date (default: today) - Specify a "Cooking Party" name (optionally) - Pick from a list of followers who does he wants to invite - See all his previous cooking parties - See who has confirm the invitation . - Receive invitations to parties through e-mail - Confirm invitations to parties without login to the website | https://trello.com/c/Zsg3X4oF
Sprint 2 | Notifications: Someone liked my recipe | 8 | AA | User should be able to: - See in the navbar an area with all his notifications - Each time he refresh the page he should see all notification until that moment - Get a notification when a user like his recipe - Do not get the notification if the user dis-like his recipe - Stop seeing notifications "number" that he already "watched" - See all his notifications even when he has already "watch" them - Mark a notification as "wached" as soon as he open the notification bar. | https://trello.com/c/hAS95Dsl
Sprint 2 | Notifications: Someone followed me | 2 | AA | User should be able to: - Get a notification when a user follow him - Do not get the notification if the user un-follow him | https://trello.com/c/4G98mfOH
Sprint 2 | Notifications: New Recipe from Chef's I follow | 2 | AA | User should be able to: - Get a notification when a user he follows post a recipe | https://trello.com/c/KZeiVvMp
Sprint 2 | Social Network: Share Recipe | 1 | CP | User should be able to: - Post a recipe to "Facebook" - Post should include a picture of the recipe and the title | https://trello.com/c/bqMLFwKF
Sprint 2 | Post Recipe: Upload pictures | 1 | CP | Add functionality to upload pictures to recipe | https://trello.com/c/aia32qWZ
Sprint 2 | Navigation Bar: Filters | 3 | CP | User should be allowed filter recipes by cuisine, appliances required, eating preference(veg/non-veg), price range and inclusion of videos Whenever filters are updated anywhere in the site this should be saved to the user profile | https://trello.com/c/d9YK72NS
Sprint 2 | Navigation Bar: Sort | 2 | CP | Add filters to the search bar for sorting by tastiness, difficulty, nutritional value. Default filters should be filters specified in user profile page. When sort parameters are changed anywhere in the site it should be saved to the user's profile
Sprint 2 | Edit Profile | 2 | CP | Allow user to edit profile information Allow user to upload picture
Notes
Members
CP | Caleb De la Cruz (cdelacru)
AA | Abishek Anand (asanand) - Product Owner
Points | Hours
1 | [0-2]
2 | [3-4]
3 | [4-6]
5 | [6-8]
8 | [8-16]