## ChillFood.com
ChillFood.com
Sprint #1 Backlog
https://trello.com/b/5tEQHZBy
List | Title | Points | Members | Description | Card URL
Sprint 1 | Login | 1 | CP | User should be able to: - Login using their email address and a password | https://trello.com/c/dNXRE3r3
Sprint 1 | Register | 1 | CP | User should be able to: - register using their email address and a password - optionally include their bio while registering - confirm their e-mail address before posting a recipe | https://trello.com/c/fNzLlqp8
Sprint 1 | Initial Dataset | 8 | AA | Create a script which: - Connects to the open source database API - Retrieve recipes with low difficulty - Separate the description in steps - Stored recipes in the PostgreSQL database - Stored pictures locally | https://trello.com/c/Zsg3X4oF
Sprint 1 | Post Recipe: Static info | 5 | CP | User should be to: - Create a recipe - Add the title of the recipe - Specify duration, kcal and video link - Add ingredients - Add Steps - Select categories - Select appliances - Save the recipe as a Draft - Publish the recipe so everybody can see it Others Task: - Fill the list of categories - Fill the list of appliances | https://trello.com/c/hAS95Dsl
Sprint 1 | Detail Recipe: Static Info | 5 | AA | User should be to: - See a recipe. The recipe should follow the layout specify in the wire-frame. - Increment the counter of the amount of views a recipe has. | https://trello.com/c/4G98mfOH
Sprint 1 | Landing Page: List of Recipes [Paginated] | 5 | CP | User should be able to: - See a list of recipes as soon as he login - The recipes should be order by amount of views - Only see the top 12 recipes - Click a button "show more" to show the next 12 recipes (and so on) - Click a recipe and go to detail page. | https://trello.com/c/KZeiVvMp
Sprint 1 | Profile Page | 2 | AA | Create user profile page viewing/editing personal information Show uploaded recipes in a list with brief description Clicking on a recipe should redirect to recipe details page | https://trello.com/c/bqMLFwKF
Sprint 1 | Detail Recipe: Comments | 3 | AA | Create functionality to add comments to a recipe Comments should be displayed below the recipe in reverse chronological order | https://trello.com/c/aia32qWZ
Sprint 1 | Navigation Bar: Search Bar | 5 | CP | Add persistent search bar to the top of every page. Add functionality for searching across recipes. User should be able to search across any text in recipe. On submit of the search text redirect user to a new page to display results. Display results in a list with brief recipe details. | https://trello.com/c/d9YK72NS
Notes
Members
CP | Caleb De la Cruz (cdelacru)
AA | Abishek Anand (asanand)
Points | Hours
1 | [0-2]
2 | [3-4]
3 | [4-6]
5 | [6-8]
8 | [8-16]

## Archived ChillFood.com
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL