## ChillFood.com
ChillFood.com
Sprint #3 Backlog
https://trello.com/b/5tEQHZBy
List | Title | Points | Members | Description
Sprint #3 | Cook of the Month: CRUD | 5 | CP | Administrator should be able to; - Set the user of the month for an specific month - See previous selected users - Update the chef of the month - Delete the chef of the month
Sprint #3 | Cook of the Month: Landing Page | 2 | CP | User should be able to see: - Who is the best cook of that month
Sprint #3 | Host app through cloud service | 13 | AA | Deploy the app on a cloud service Test all features to ensure they are working as expected
Sprint #3 | Edit Profile | 2 | CP | Allow user to edit profile information Allow user to upload picture
Sprint #3 | Detail Recipe: Video Streaming | 2 | CP | User should be able to: - Include a youtube link to its recipe - See youtube video on the site
Sprint #3 | Social Network: Register/Login | 5 | CP | User should be able to: - Register using facebook - Login using facebook
Sprint #3 | Upload recipe images to cloud service | 3 | AA | Images downloaded from the API are saved to the local machine. These need to be uploaded to a cloud service
Sprint #3 | Unit Test api.py | 8 | CP
Sprint #3 | Unit Test views.py | 8 | AA
Sprint #3 | Count page views | 1 | AA
Sprint #3 | Notifications for cooking party | 1 | AA
Notes
Members
CP | Caleb De la Cruz (cdelacru) - Product Owner
AA | Abishek Anand (asanand)
Points | Hours
1 | [0-2]
2 | [3-4]
3 | [4-6]
5 | [6-8]
8 | [8-16]